## Sheet1
Bug ID | Bug Title | Status
Bug-001 | Content cut on laptop screen | Open
Bug-002 | Load optimization issue | Open
Bug-003 | Content not same on B2B SaaS Development section from app development landing page. | Open
Bug-004 | Technology stack badge missing on the Entertainment / Ecommerce / Staffing page. | Open
Bug-005 | Remove database section on the Entertainment page. | Open
Bug-006 | The technology stack is missing on the Entertainment page. | Open
Bug-007 | Content not same as document on the Ecommerce page. | Open
Bug-008 | Badge should be changed on the Ecommerce page. | Open
Bug-009 | Content not same on the Ecommerce page. | Open
Bug-010 | Content not same on the Ecommerce page. | Open
Bug-011 | Content not same as the document on the Ecommerce page. | Open
Bug-012 | When hovering over Industries, the Services dropdown moves up and down, even though the cursor is not hovering over it. | Backlog
Bug-013 | Maze logo apply animation (as per reference website) | Backlog
Bug-014 | Button animation not appearing in mobile responsive mode | Backlog
Bug-015 | Card text alignment issue on UI/UX page | Backlog
Bug-016 | Add link (Get in Touch button) should be home page. | In Progress
Bug-017 | The "Book a Free Call" button does not have a Calendly URL linked. Clicking the button does not redirect to the page. | In Progress
Bug-018 | Recent blog images should be added in menu dropdown. | In Progress
Bug-019 | Subscribe button API not integrated on blog detail page. | In Progress
Bug-020 | Text color not same as Figma design (We Work section) | Done
Bug-021 | Get in Touch button not visible on mobile view | Done
Bug-022 | Social media icons not visible on mobile view | Done
Bug-023 | Peptide logo missing | Done
Bug-024 | Favicon is missing | Done
Bug-025 | Dropdown icons missing in Services, Insight, and Industries menu | Done
Bug-026 | Background color of Trusted by 50+ section not matching the design. | Done
Bug-027 | Replace Rick Sandine logo with Alpha Arc logo | Done
Bug-028 | Remove shadow from WorkSafe Mapping image | Done
Bug-029 | In Get Our Services card, background colors of iOS, Android, and UX Design buttons are not consistent. | Done
Bug-030 | Background color of Product Designers section not matching the design. | Done
Bug-031 | Development emoji is different from the design. | Done
Bug-032 | Submit button size not consistent across sections. | Done
Bug-033 | Image alignment in Latest Insight section not matching the design (Home page) | Done
Bug-034 | Background color of Frequently Asked Questions section not matching the design. | Done
Bug-035 | Background shadow in We Design and Build Digital Products section not consistent with the design. | Done
Bug-036 | Footer line is incomplete. | Done
Bug-037 | Mail icon in Get in Touch section not matching the design. | Done
Bug-038 | Spelling mistake in D-U-N-S Registered text. | Done
Bug-039 | Missing space between phone number and email in the header. | Done
Bug-040 | Black line appearing in mobile navigation menu. | Done
Bug-041 | Spelling mistake in the "Get a Quote" button text. | Done
Bug-042 | Mobile. | Done
Bug-043 | Get in Touch button text color not matching the design. | Done
Bug-044 | WorkSafe Mapping image is different from the design (Home page in mobile responsive). | Done
Bug-045 | Project description text is getting cut off (Home page). | Done
Bug-046 | Descriptions for Peptide MD and Mitra Fresh Botanicals not matching the design. | Done
Bug-047 | We are a Software Development Company section is overlapping or misaligned on the screen (Home page). | Done
Bug-048 | View All Blogs text color not matching the design. | Done
Bug-049 | View All Blogs icon is missing. | Done
Bug-050 | Starting arrow appears disabled on slider section. | Done
Bug-051 | Vybe logo appears smaller compared to design in App Development. | Done
Bug-052 | Heading missing center alignment lines. | Done
Bug-053 | Pictures do not match the Figma design. | Done
Bug-054 | Footer text in Services modules does not match the design. | Done
Bug-055 | Social icon color is not same as design. | Done
Bug-056 | Dropdown arrow does not match the design. | Done
Bug-057 | Text overlaps the picture in the "Industries We Serve" section. | Done
Bug-058 | Book a Free Call and "View Our Work" buttons misaligned (displayed vertically instead of side by side). | Done
Bug-059 | Text is not centered properly. | Done
Bug-060 | The logo and text in the "Mitra Fresh Botanicals" section are misaligned. | Done
Bug-061 | Web Development badge/button appears too large on mobile view. | Done
Bug-062 | The footer layout does not match the design. | Done
Bug-063 | The "Maze Digital" logo does not redirect to the main page. | Done
Bug-064 | The social media icons are not linked to their respective pages (Footer). | Done
Bug-065 | Dropdown text highlight inconsistent for "Service" menu item. | Done
Bug-066 | The phone number input does not open a numeric keypad on mobile devices. | Done
Bug-067 | The country selection dropdown does not display all country flags. | Done
Bug-068 | Submit button text size should be 18px as per design. | Done
Bug-069 | Remove shadow. | Done
Bug-070 | Industries We Serve section slider not working / images not sliding. | Done
Bug-071 | Start Your Project button in Services section shows unwanted shadow. | Done
Bug-072 | Maze Digital website footer: Maze Digital logo and D-U-N-S Registered icon touching text/divider lines (spacing issue). | Done
Bug-073 | The page loads at a random middle position instead of starting at the top after refresh. | Done
Bug-074 | Unexpected highlighting appears in Insight. | Done
Bug-075 | Screen zooms in when switching iPad orientation from landscape to portrait. | Done
Bug-076 | Get in Touch section icon size does not match the design. | Done
Bug-077 | All sections show the same "Year of Experience" text, which does not match the design. | Done
Bug-078 | Paragraph spacing incorrect. | Done
Bug-079 | Chief Executive Officer title missing in Meet Our Team section. | Done
Bug-080 | Phone number country code displayed even though it is not shown in the design. | Done
Bug-081 | Terms and Conditions / Privacy Policy text missing in footer. | Done
Bug-082 | The Maze Digital logo in the footer is touching the line above it. | Done
Bug-083 | Happy client images not displaying (Main page). | Done
Bug-084 | Social icon size does not match design (Footer). | Done
Bug-085 | Text color is not same as design. | Done
Bug-086 | Text size inconsistency (Home page). | Done
Bug-087 | Text size mismatch with design (Services pages). | Done
Bug-088 | Text size inconsistency (Home page). | Done
Bug-089 | Our mobile development services heading text inconsistency. | Done
Bug-090 | Industries We Serve heading text size and color inconsistency (Services pages). | Done
Bug-091 | Responsiveness issue. | Done
Bug-092 | App Development section does not match design. | Done
Bug-093 | Web Development section is incorrect. | Done
Bug-094 | UI/UX section background does not match design. | Done
Bug-095 | B2B SaaS section does not match design. | Done
Bug-096 | MVP Development section does not match design. | Done
Bug-097 | The service page links in the website footer are not clickable. | Done
Bug-098 | Text size is inconsistent and does not follow the design. | Done
Bug-099 | Text size inconsistency. | Done
Bug-100 | Explore Topics heading does not match the design. | Done
Bug-101 | Font inconsistency. | Done
Bug-102 | The picture displayed in the Explore Topics section does not match the design. | Done
Bug-103 | Text size inconsistency. | Done
Bug-104 | Footer navigation does not work correctly from Explore Topics pages. | Done
Bug-105 | Text size and color do not match the design. | Done
Bug-106 | Font inconsistency. | Done
Bug-107 | Text size and color inconsistency. | Done
Bug-108 | The "Follow" and "Key Points" headings are not aligned on the same line. | Done
Bug-109 | Text size inconsistency. | Done
Bug-110 | Blog detail page font inconsistency. | Done
Bug-111 | Subscribe text inconsistency. | Done
Bug-112 | Font inconsistency. | Done
Bug-113 | Size should match the design. | Done
Bug-114 | Related blogs font inconsistency. | Done
Bug-115 | View All text inconsistency. | Done
Bug-116 | Related blog section pictures do not match the design. | Done
Bug-117 | Incorrect location showing for Pakistan. | Done
Bug-118 | Text size inconsistency. | Done
Bug-119 | Submit text inconsistency. | Done
Bug-120 | Heading color not matching design. | Done
Bug-121 | Text size inconsistency. | Done
Bug-122 | Text size inconsistency. | Done
Bug-123 | Text color issue on Privacy Policy page. | Done
Bug-124 | Text size issue. | Done
Bug-125 | Use of Information content text issue. | Done
Bug-126 | Date should be on a new line. | Done
Bug-127 | Phone number input field cursor jumps while deleting digits. | Done
Bug-128 | Terms & Conditions / Privacy Policy not clickable on mobile. | Done
Bug-129 | Organization and Region fields missing in Got a Project. | Done
Bug-130 | Privacy Policy not clickable in the "Got a Project" section. | Done
Bug-131 | Unwanted horizontal line appearing above social media icons. | Done
Bug-132 | Unnecessary bottom spacing and missing gaps between menu items. | Done
Bug-133 | Text size should match the design. | Done
Bug-134 | Text color issue on Career detail page. | Done
Bug-135 | White screen appears on the header background, which does not match the design. | Done
Bug-136 | Text size should match the design. | Done
Bug-137 | Font issue. | Done
Bug-138 | Button text does not match the design. | Done
Bug-139 | Button size does not match the design. | Done
Bug-140 | Picture corners not curved as per design. | Done
Bug-141 | Font issue. | Done
Bug-142 | Text mismatch with design. | Done
Bug-143 | Dummy text should be removed. | Done
Bug-144 | Text size and color should match the design. | Done
Bug-145 | Text size and color on Career page do not match the design. | Done
Bug-146 | Size issue does not match the design. | Done
Bug-147 | Font issue in Open Opportunities heading and sub-content. | Done
Bug-148 | Background gradient missing. | Done
Bug-149 | See More text size and color issue. | Done
Bug-150 | Text color issue. | Done
Bug-151 | Page scroll position changes unexpectedly on refresh. | Done
Bug-152 | Screen zooms when typing in a text field. | Done
Bug-153 | Content cut off from top and bottom on iOS Safari. | Done
Bug-154 | Heading text incorrect break / alignment issue. | Done
Bug-155 | Text color inconsistency. | Done
Bug-156 | Text size inconsistency. | Done
Bug-157 | Text color inconsistency. | Done
Bug-158 | Dropdown closes automatically when scrolling the page. | Done
Bug-159 | Add a Coming Soon page on the Testimonials page, similar to the Industries page. | Done
Bug-160 | Current section design does not match the expected design. | Done
Bug-161 | The "Tell us about Your project" input field is missing from the Got a Project section form. | Done
Bug-162 | Remove category text heading in all services pages. | Done
Bug-163 | Add link ("Get in Touch" button) to every Services page (App Development, B2B SaaS, Web Development, MVP Development, Design & UX). | Done
Bug-164 | Text color issue in Careers page. | Done
Bug-165 | Text color issue in Careers page. | Done
Bug-166 | See More text color issue in Careers page. | Done
Bug-167 | Page scroll position changes unexpectedly on refresh (Blogs → Detail page). | Done
Bug-168 | Text spacing inconsistency on Services & Insights dropdown pages. | Done
Bug-169 | Footer social icons are hidden (likely a padding or viewport height issue on mobile). | Done
Bug-170 | Text size should match the design. | Done
Bug-171 | Header should match the design. | Done
Bug-172 | Text size should match the design on the AI page. | Done
Bug-173 | The line is not centered on the AI page. | Done
Bug-174 | Text size does not match the design on the AI page. | Done
Bug-175 | Industries We Serve text size does not match the design. | Done
Bug-176 | The "Get in Touch" button size does not match the design (196 × 56). | Done
Bug-177 | Get in Touch text size does not match the design. | Done
Bug-178 | Icon size does not match the design. | Done
Bug-179 | Content should match the design. | Done
Bug-180 | Read Case Study text size inconsistency on AI page. | Done
Bug-181 | Heading text size inconsistency. | Done
Bug-182 | We help... content text size and color should match the design. | Done
Bug-183 | Heading text size and color should match the design. | Done
Bug-184 | Background color should match the design on AI pages. | Done
Bug-185 | Text color should match the design. | Done
Bug-186 | Text color does not match the design. | Done
Bug-187 | Content should match the design. | Done
Bug-188 | The "Book a Free Call" button is touching the section below. | Done
Bug-189 | This section should also be updated on the Home page. | Done
Bug-190 | Clicking the "Get a Quote" button redirects to the "Got a Project" page on Home. | Done
Bug-191 | No underline appears on hover, and the cursor does not change. | Done
Bug-192 | Remove "Select" text from the Get in Touch form. | Done
Bug-193 | Background color and size do not match the Healthcare page design. | Done
Bug-194 | Missing section(s) on the Healthcare page. | Done
Bug-195 | Image section size does not match the Healthcare page design. | Done
Bug-196 | The "Peptide…" text size does not match the Healthcare page design. | Done
Bug-197 | Text size is not consistent with the Healthcare page design. | Done
Bug-198 | Slider is not displayed. | Done
Bug-199 | Content differs from the Healthcare page design. | Done
Bug-200 | This section is also missing on the Healthcare page. | Done
Bug-201 | Section color differs from the Healthcare page design. | Done
Bug-202 | The FAQ section does not display the full form of FAQ, and its text color does not match the design. | Done
Bug-203 | Some text colors do not match the design on the Healthcare page. | Done
Bug-204 | Text color inconsistency in the Question & Answer section on the Healthcare page. | Done
Bug-205 | Footer content differs from the Healthcare page design. | Done
Bug-206 | Button background color does not match the design. | Done
Bug-207 | One or more sections are missing from the Construction page. | Done
Bug-208 | Heading content is inconsistent. | Done
Bug-209 | Images are not displaying on the Healthcare page. | Done
Bug-210 | Text color inconsistency on the Healthcare page. | Done
Bug-211 | Text size and color inconsistency on the Healthcare page. | Done
Bug-212 | First and last image sizes do not match the design. | Done
Bug-213 | Text color inconsistency on the Ecommerce page. | Done
Bug-214 | We build... content text size and color inconsistency on the Ecommerce page. | Done
Bug-215 | Image size inconsistency on the Ecommerce page. | Done
Bug-216 | Text size inconsistency on the Ecommerce page. | Done
Bug-217 | Content does not match the design on the Ecommerce page. | Done
Bug-218 | Image size inconsistency on the Ecommerce page. | Done
Bug-219 | Mobile text is missing. | Done
Bug-220 | Text color inconsistency on the Ecommerce page. | Done
Bug-221 | Text color inconsistency on the Ecommerce page. | Done
Bug-222 | Background color inconsistency on the Ecommerce page. | Done
Bug-223 | Text does not match the design (Industries - All Pages). | Done
Bug-224 | Displayed content differs from the design on the Ecommerce page. | Done
Bug-225 | Text color inconsistency on Healthcare, Construction, Ecommerce, Entertainment, and Staffing pages. | Done
Bug-226 | Icon size does not match the design. | Done
Bug-227 | Image does not match the design on the Staffing page. | Done
Bug-228 | Content does not match the design on the Staffing page. | Done
Bug-229 | Content does not match the design on the Staffing page. | Done
Bug-230 | Remove the "I" character on the Healthcare page. | Done
Bug-231 | Headings on Industries sub-pages are not properly aligned. | Done
Bug-232 | Content does not match the design on the Healthcare page. | Done
Bug-233 | Images are cut off on the B2B SaaS page. | Done
Bug-234 | Book a Free Call background color does not match the design on the B2B SaaS page. | Done
Bug-235 | UI/UX text does not match the design. | Done
Bug-236 | Text color mismatch with the design (All Services pages). | Done
Bug-237 | Web text is missing. | Done
Bug-238 | WorkSafe Mapping text should display a hand cursor on hover. | Done
Bug-239 | Icons are displayed, but the circle animation is not visible. | Done
Bug-240 | View All Blogs should link to the Blogs page. | Done
Bug-241 | Get a Quote button is not fully clickable on the Home page. | Done
Bug-242 | Every dark background button should be animated. | Done
Bug-243 | Remove the Canada address from the Contact Us page. | Done
Bug-244 | Footer year should be auto-generated. | Done
Bug-245 | Add validation to all forms. | Done
Bug-246 | Got a Project form should be updated. | Done
Bug-247 | Add extra spacing to the top and bottom of the Projects and Testimonials pages. | Done
Bug-248 | Add spacing between "both" and "depending". | Done
Bug-249 | Clicking social icons highlights "Terms & Conditions". | Done
Bug-250 | Add the link to "80 Reviews". | Done
Bug-251 | Country flag is not changing dynamically and shows the default/incorrect flag. | Done
Bug-252 | View Our Work button should redirect to the Success Stories section (All Services pages). | Done
Bug-253 | Services section slider does not move with mouse interaction (All Services pages). | Done
Bug-254 | Start Your Project link is missing (All Services pages). | Done
Bug-255 | Sliders on Industries sub-pages are visible but do not move with mouse interaction. | Done
Bug-256 | Alignment issues on Industries sub-page sliders (headings and descriptions are not properly aligned). | Done
Bug-257 | Cards on Industries sub-pages are not clickable and have no links. | Done
Bug-258 | Incorrect LinkedIn links in the "Meet Our Team" section on the About Us page. | Done
Bug-259 | Text alignment issue on cards in the Careers page. | Done
Bug-260 | Navigation is missing on the Careers page ("View Open Positions" button has no link). | Done
Bug-261 | Incorrect job title displayed on the Open Opportunities page (Software Quality Assurance shown instead of UI/UX Designer). | Done
Bug-262 | Content should be left-aligned to match the design (Industries - All Pages). | Done
Bug-263 | Remove scrolling from the "Got a Project" side drawer. | Done
Bug-264 | Content should be aligned (All Services pages). | Done
Bug-265 | View All Blogs button should match the design (Home page). | Done
Bug-266 | Footer year should be auto-generated. | Done
Bug-267 | Footer social links are not working. | Done
Bug-268 | Heading content does not match the images or design. | Done
Bug-269 | Background page scrolling is not disabled when the "Got a Project" side drawer is open. | Done
Bug-270 | Phone Number and Tell us about the project fields should also be highlighted. | Done
Bug-271 | Incorrect text: UI UX should be UI/UX (Career page) | Done
Bug-272 | Text is cut off on mobile devices (Industries All pages) | Done
Bug-273 | On the Industries pages, when the screen size is minimized, a white space appears on the side. | Done
Bug-274 | After hovering, this content should appear as shown in the design (Industries All pages) | Done
Bug-275 | When selecting a country flag, the corresponding country code is not being added/displayed along with it. | Done
Bug-276 | Field-wise validation not working separately (Form page) | Done
Bug-277 | Email text should be clickable link wherever displayed. | Done
Bug-278 | Testimonials page should be removed from the application, and the Projects section should be commented out for now. | Done
Bug-279 | Apply this marquee animation for given picture. | Done
Bug-280 | Add the image sections to have the same animation as the links. | Done
Bug-281 | Hand cursor should be on whole section. | Done
Bug-282 | Country code removed after entering name and email fields. | Done
Bug-283 | The form is getting submitted successfully even when the phone number field is empty. | Done
Bug-284 | Phone number should be linked. | Done
Bug-285 | This section should also have a link, same as the other linked sections. Currently, it is not clickable. | Done
Bug-286 | The hand (pointer) cursor should appear when hovering over every button. Currently, some buttons do not show the pointer cursor on hover. | Done
Bug-287 | After sending the email, the success message currently shows "Email sent successfully". This text should be changed to: "Thank you for contacting us". | Done
Bug-288 | After submitting the form once, the success message "Email sent successfully" appears. If the user clicks the Submit button again, the success message does not get removed/reset and still remains visible. | Done
Bug-289 | Footer location address need to be updated. | Done
Bug-290 | Latest insights section (Whole website) | Done
Bug-291 | In the "What We Do Best" section, the items are not linked to their respective pages. | Done
Bug-292 | Images are being cut to fit the screen size, but they should display fully without cropping. | Done
Bug-293 | The "Tell us about your project" field in the form does not have validation. | Done
Bug-294 | Arrow should match the design. | Done
Bug-295 | Remove the phone number digit limit in form. | Done
Bug-296 | Add animation to Employees and Happy Clients numbers. | Done
Bug-297 | View All Blogs button not linked on home page. | Done
Bug-298 | Add "100+" number in Happy Clients. | Done
Bug-299 | The icons in the "Discover Other Industries" section are not loading properly. | Done
Bug-300 | Alpha Arc logo should be changed. | Done
Bug-301 | Remove Mitra Fresh and Shynda Achille logos on main page. | Done
Bug-302 | View Our Work button should redirect to the Success Stories section (All Industries pages). | Done
Bug-303 | In the mobile responsive version, the Project and Testimonials pages should also be removed. | Done
Bug-304 | Add animation. | Done
Bug-305 | Remove Twitter icon on mobile responsive. | Done
Bug-306 | Reduce spacing. | Done
Bug-307 | FAQ questions should animate on hover and change color. | Done
Bug-308 | Button animation. | Done
Bug-309 | Latest Insights page redirects incorrectly. | Done
Bug-310 | Remove Mitra logo from this section. | Done
Bug-311 | Text color does not change on hover over image text. | Done
Bug-312 | Add text. | Done
Bug-313 | Tell us about your project text field size does not match the design. | Done
Bug-314 | Add underline in header and form email/phone number. | Done
Bug-315 | Finger pointer cursor should be applied to the entire website. | Done
Bug-316 | The logo appears blurry or low resolution. | Done
Bug-317 | Only text flips on the "Book a Free Call" button. | Done
Bug-318 | The header background should remain white after navigating back from the form page. | Done
Bug-319 | Grey bar displayed on phone number field during API call instead of loader. | Done
Bug-320 | The Employees section does not load fully and is not displayed correctly with proper alignment and spacing on mobile devices. | Done
Bug-321 | The logo loads late or shows a delay before appearing properly. | Done
Bug-322 | Remove animation from "Submit" and "Get a Quote" buttons. | Done
Bug-323 | Remove shadow animation from "Book a Call" button on hover. | Done
Bug-324 | Career page responsive issue. | Done
Bug-325 | When I zoom in, the screen starts fluctuating on the home page. | Done
Bug-326 | Mobile responsive button issue. | Done
Bug-327 | A screen recording–like animation appears in all subsections of Services and Insights. | Done
Bug-328 | Remove this box shadow on the Careers page. | Done
Bug-329 | No need for hand cursor on Careers section. | Done
Bug-330 | This section should be updated on the Home page. | Done
Bug-331 | Auto-scroll missing for Key Impact content on Industries pages. | Done
Bug-332 | Remove "Read Case Study" button. | Done
Bug-333 | Founder or client name missing on second testimonial videos. | Done
Bug-334 | Remove this video on the Home page. | Done
Bug-335 | Upon clicking the video, it should open exactly as shown in the provided screen recording (full video view). | Done
Bug-336 | Hand cursor not appearing on Play button icon. | Done
Bug-337 | Slider button should be disabled. | Done
Bug-338 | In mobile responsive view, the video play icon does not match the design. | Done
Bug-339 | Services pages should also be updated in the Testimonials section. | Done
Bug-340 | Image issue on Blogs page. | Done
Bug-341 | The background color should match the design on the Blogs page. | Done
Bug-342 | The Twitter icon should be removed from the Blog Detail page. | Done
Bug-343 | The social icons should be linked on the Blog Detail page. | Done
Bug-344 | Replace "Submit" button text with "Subscribe". | Done
Bug-345 | Add animation on the Blog Detail page like other pages. | Done
Bug-346 | The validation message should appear exactly like it does on the Home page. | Done
Bug-347 | No animation is applied to the "See More" button on the Careers page. | Done
Bug-348 | No animation is applied to the "View Detail" button on the Careers page. | Done
Bug-349 | Validation error messages should appear directly below the corresponding input field. | Done
Bug-350 | Line animation should be removed from white background buttons. | Done
Bug-351 | Add animation this button on industry pages | Done
Bug-352 | Text on the page does not match the design in ecommerce page | Done
Bug-353 | Text on the page does not match the design on ecommerce page | Done
Bug-354 | Text on the page does not match the design on entertainment page | Done
Bug-355 | Case study button is missing on e-commerce and entertainment pages. | Done
Bug-356 | Text on the page does not match the design on construction page | Done
Bug-357 | Text on the page does not match the design on staffing page | Done
Bug-358 | In mobile responsive development tag direction not same as design in blogs page | Done
Bug-359 | Text on the blogs detail page does not match the design | Done
Bug-360 | Careers Page text animation same as AI page | Done
Bug-361 | Drawer should not open on "Read Case Study" button in whole website | Done
Bug-362 | Responsive issue | Done
Bug-363 | Hand cursor on other categories section in blogs detailed page | Done
Bug-364 | Remove AI tage on blogs deatil page | Done
Bug-365 | Change Animation on Industries pages | Done
Bug-366 | Update Industries main animation to match insights section highlight | Done
Bug-367 | Meet our team section animaton should also be change like blog section | Done
Bug-368 | Blog detail page date format should match design | Done
Bug-369 | View all text color shoud be change on blog detail page | Done
Bug-370 | Missing slash in (UI/UX) text on blogs detail page | Done
Bug-371 | Remove hand cursor and text color change on section | Done
Bug-372 | Remove shadow industries all sub pages | Done
Bug-373 | Update testimonials section on main page | Done
Bug-374 | Change animation like header on this page section | Done
Bug-375 | All text removed | Done
Bug-376 | Remove this text animation on industries sub pages | Done
Bug-377 | Remove scroller on our staffing solutions in industries sub pages | Done
Bug-378 | Add animation on construction and staffing page | Done
Bug-379 | Add animation open opportunities text on careers page | Done
Bug-380 | Alpha arc icon or text alignment not matched on design (MVP Development page) | Done
Bug-381 | Missing Tabs in B2B SaaS, and MVP Development Sections | Done
Bug-382 | Heading should be changed on (Services --> UI/UX page) | Done
Bug-383 | Change testimonials videos | Done
Bug-384 | Incorrect tab display under web development section | Done
Bug-385 | Play icon button not match on website in mobile responsive view | Done
Bug-386 | Text heading change according to Document (All Services pages) | Done
Bug-387 | Heading text changes to All Services Pages | Done
Bug-388 | Learn more starting text should be capital in All services pages | Done
Bug-389 | Text changes on web Page | Done
Bug-390 | Remove Get a quote and Book a meeting button | Done
Bug-391 | In Home page "We Build Digital" section alignment issue | Done
Bug-392 | In who we are section 98% content missing on home page | Done
Bug-393 | Text change | Done
Bug-394 | Our work text missing in app development page | Done
Bug-395 | Content missing on app development page | Done
Bug-396 | Why Maze Digital section appears after "View All Case Studies" Button | Done
Bug-397 | Client reviews section appears after "Why Maze Digital" Button section | Done
Bug-398 | SowEasy image should be change according to design on project page | Done
Bug-399 | In Design tool section missing badges on UI/UX page | Done
Bug-400 | Icon color missing on High-Fidelity UI Design section on UI/UX Page | Done
Bug-401 | Rocket fire missing on UI/UX page (see images) | Done
Bug-402 | How we think section images not same as design on UI/UX page | Done
Bug-403 | In footer content does not match design on UI/UX page | Done
Bug-404 | Text change in MVP page | Done
Bug-405 | Badge text change on MVP page | Done
Bug-406 | Heading text change on MVP page | Done
Bug-407 | Heading content change on MVP page like design | Done
Bug-408 | Heading text change on MVP page | Done
Bug-409 | Core notification content change like design on MVP page | Done
Bug-410 | Icon color not same as design on MVP page | Done
Bug-411 | Icon Rocket fire missing on MVP page | Done
Bug-412 | Text change on MVP page | Done
Bug-413 | Heading content text change on MVP page | Done
Bug-414 | Text content change on MVP page | Done
Bug-415 | Text content not like design | Done
Bug-416 | Startup insights badge add on MVP Page | Done
Bug-417 | Text content not same as design on MVP page | Done
Bug-418 | Number and text color not same as design on case studies page | Done
Bug-419 | Footer content not same as design on peptide case studies page | Done
Bug-420 | Number text color not same as design on Inspo Hair case studies page | Done
Bug-421 | Footer text not same as design on Inspo Hair case study page | Done
Bug-422 | Screen blinks after closing form opened by Book a Free Call button. | Done
Bug-423 | Badges missing on B2B SaaS page in Architecture pillars section. | Done
Bug-424 | Content not same as design on B2B SaaS page in Why Maze Digital section. | Done
Bug-425 | Icon color not same as design on B2B SaaS page in Our Process section. | Done
Bug-426 | Rocket icon not same as design on B2B SaaS page in Our Process section. | Done
Bug-427 | Content not same as design on B2B SaaS page. | Done
Bug-428 | Steri Pass content replace with Taco Jose Web Platform on B2B SaaS page. | Done
Bug-429 | Remove this client images on B2B SaaS page. | Done
Bug-430 | Badge missing on AI page. | Done
Bug-431 | Released date not same as LLM section guide as document on AI page. | Done
Bug-432 | AI development insight badge missing on AI page. | Done
Bug-433 | Our story content is repeating paragraph 2 times on About page. | Done
Bug-434 | Heading text change on About page. | Done
Bug-435 | Alignment issue text or images on About page. | Done
Bug-436 | Two questions more add on FAQ section in About page. | Done
Bug-437 | Content not same as design on Careers page. | Done
Bug-438 | Click on View All Case Studies button then open Case Studies page. | Done
Bug-439 | If you have peptide case study then Read Case Study button clickable on Healthcare page. | Done
Bug-440 | About the app content not same as design on Beyond Therapy AI. | Done
Bug-441 | Tech Stack we use in Beyond Therapy AI section content not exact same as design. | Done
Bug-442 | Remove WhAWS text on Healthcare page. | Done
Bug-443 | Add question mark on Healthcare page. | Done
Bug-444 | Update heading of FAQ section on Healthcare page. | Done
Bug-445 | AI “I” should be capitalized in Healthcare page. | Done
Bug-446 | Content not same as document on Construction page. | Done
Bug-447 | Content is missing on Construction page. | Done
Bug-448 | Dart & React Native icons not displaying correctly on all Industries pages. | Done
Bug-449 | Content and image mismatch on Entertainment page. | Done
Bug-450 | Content not same as design on Entertainment page. | Done
Bug-451 | Section missing on Entertainment page. | Done
Bug-452 | Content from the Entertainment page is not displayed in the "We Build" section. | Done
Bug-453 | Content not same as design on Entertainment page. | Done
Bug-454 | Content does not match the design on the Entertainment page. | Done
Bug-455 | This section is not same as design on the Entertainment page. | Done
Bug-456 | Remove this line from the FAQ section on all Industries pages. | Done
Bug-457 | FAQ section not same as design on Entertainment page. | Done
Bug-458 | FAQ section not same as document on App Development landing page. | Done
Bug-459 | FAQ section not same as document on App Development landing page. | Done
Bug-460 | Client reviews of John Doe do not match the document on the landing page. | Done
Bug-461 | Button text not same as document on Social landing page. | Done